## Live Gantt Tracker
Style Name: | America
Dispatch Date: | 2026-04-30
Today:
Activity | Planned Start | Planned End | Duration | Start Offset | Status
Order receipt (Buyer PO) | 2026-03-09 | 2026-03-11 | 2 | 0
Consumption calculation | 2026-03-11 | 2026-03-13 | 2 | 2
BOM generation | 2026-03-13 | 2026-03-15 | 2 | 4
PO issue for Fabric, trims | 2026-03-15 | 2026-03-18 | 3 | 6
Size set submission | 2026-03-18 | 2026-03-21 | 3 | 9
Size set Comments | 2026-03-21 | 2026-03-23 | 2 | 12
PP meeting | 2026-03-23 | 2026-03-24 | 1 | 14
Production planning updates and circulation | 2026-03-24 | 2026-03-25 | 1 | 15
Fabric in-house | 2026-03-25 | 2026-04-02 | 8 | 16
Trims In-house | 2026-04-02 | 2026-04-05 | 3 | 24
Cutting | 2026-04-05 | 2026-04-07 | 2 | 27
Fabrication/stitching | 2026-04-07 | 2026-04-22 | 15 | 29
Finishing | 2026-04-22 | 2026-04-25 | 3 | 44
Packing | 2026-04-25 | 2026-04-27 | 2 | 47
Inspection | 2026-04-27 | 2026-04-29 | 2 | 49
Dispatch | 2026-04-29 | 2026-04-30 | 1 | 51
Formulas:
Status = IF([Planned Start]-TODAY()<0,"Delayed",IF([Planned Start]-TODAY()<=10,"Risk","On Track"))