## Live Gantt Tracker
Style Name: | Ashwin
Dispatch Date: | 2026-03-26
Today:
Activity | Planned Start | Planned End | Duration | Start Offset | Status
Order receipt (Buyer PO) | 2026-02-08 | 2026-02-10 | 2 | 0
Consumption calculation | 2026-02-10 | 2026-02-12 | 2 | 2
BOM generation | 2026-02-12 | 2026-02-14 | 2 | 4
PO issue for Fabric, trims | 2026-02-14 | 2026-02-16 | 2 | 6
Size set submission | 2026-02-16 | 2026-02-18 | 2 | 8
Size set Comments | 2026-02-18 | 2026-02-20 | 2 | 10
PP meeting | 2026-02-20 | 2026-02-22 | 2 | 12
Production planning updates and circulation | 2026-02-22 | 2026-02-24 | 2 | 14
Fabric in-house | 2026-02-24 | 2026-03-04 | 8 | 16
Trims In-house | 2026-03-04 | 2026-03-06 | 2 | 24
Cutting | 2026-03-06 | 2026-03-08 | 2 | 26
Fabrication/stitching | 2026-03-08 | 2026-03-18 | 10 | 28
Finishing | 2026-03-18 | 2026-03-20 | 2 | 38
Packing | 2026-03-20 | 2026-03-22 | 2 | 40
Inspection | 2026-03-22 | 2026-03-24 | 2 | 42
Dispatch | 2026-03-24 | 2026-03-26 | 2 | 44
Formulas:
Status = IF([Planned Start]-TODAY()<0,"Delayed",IF([Planned Start]-TODAY()<=10,"Risk","On Track"))