## Live Gantt Tracker
Style Name: | Sonna
Dispatch Date: | 2026-05-20
Today:
Activity | Planned Start | Planned End | Duration | Start Offset | Status
Order receipt (Buyer PO) | 2026-03-30 | 2026-04-01 | 2 | 0
Consumption calculation | 2026-04-01 | 2026-04-03 | 2 | 2
BOM generation | 2026-04-03 | 2026-04-05 | 2 | 4
PO issue for Fabric, trims | 2026-04-05 | 2026-04-07 | 2 | 6
Size set submission | 2026-04-07 | 2026-04-09 | 2 | 8
Size set Comments | 2026-04-09 | 2026-04-11 | 2 | 10
PP meeting | 2026-04-11 | 2026-04-13 | 2 | 12
Production planning updates and circulation | 2026-04-13 | 2026-04-15 | 2 | 14
Fabric in-house | 2026-04-15 | 2026-04-23 | 8 | 16
Trims In-house | 2026-04-23 | 2026-04-25 | 2 | 24
Cutting | 2026-04-25 | 2026-04-27 | 2 | 26
Fabrication/stitching | 2026-04-27 | 2026-05-12 | 15 | 28
Finishing | 2026-05-12 | 2026-05-14 | 2 | 43
Packing | 2026-05-14 | 2026-05-16 | 2 | 45
Inspection | 2026-05-16 | 2026-05-18 | 2 | 47
Dispatch | 2026-05-18 | 2026-05-20 | 2 | 49
Formulas:
Status = IF([Planned Start]-TODAY()<0,"Delayed",IF([Planned Start]-TODAY()<=10,"Risk","On Track"))