## T&A Calendar
Style Name: | Perop
GSM: | 260
Order Qty: | 7200
Cut Qty (7% Extra): | 7704
Activity | Planned Start | Planned End | Actual Start | Actual End
Order receipt (Buyer PO) | 2026-04-23 | 2026-06-22
Consumption calculation | 2026-04-23 | 2026-06-17
BOM generation | 2026-04-23 | 2026-06-15
PO issue for Fabric, trims | 2026-04-23 | 2026-06-12
Size set submission | 2026-04-23 | 2026-06-07
Size set Comments | 2026-04-23 | 2026-06-04
PP meeting | 2026-04-23 | 2026-06-02
Production planning updates and circulation | 2026-04-23 | 2026-05-31
Fabric in-house | 2026-04-23 | 2026-05-23
Trims In-house | 2026-04-23 | 2026-05-18
Cutting | 2026-04-23 | 2026-05-08
Fabrication/stitching | 2026-04-23 | 2026-05-03
Finishing | 2026-04-23 | 2026-04-30
Packing | 2026-04-23 | 2026-04-28
Inspection | 2026-04-23 | 2026-04-26
Dispatch | 2026-04-23 | 2026-04-23