## T&A Calendar
Style Name: | Polo
GSM: | 180
Order Qty: | 5000
Cut Qty (7% Extra): | 5350
Activity | Planned Start | Planned End | Planned Duration (Days) | Actual Start | Actual End | Actual Duration (Days)
Order receipt (Buyer PO) | 2026-03-07 | 2026-03-09 | 2
Consumption calculation | 2026-03-09 | 2026-03-11 | 2
BOM generation | 2026-03-11 | 2026-03-13 | 2
PO issue for Fabric, trims | 2026-03-13 | 2026-03-16 | 3
Size set submission | 2026-03-16 | 2026-03-19 | 3
Size set Comments | 2026-03-19 | 2026-03-21 | 2
PP meeting | 2026-03-21 | 2026-03-22 | 1
Production planning updates and circulation | 2026-03-22 | 2026-03-23 | 1
Fabric in-house | 2026-03-23 | 2026-03-31 | 8
Trims In-house | 2026-03-31 | 2026-04-03 | 3
Cutting | 2026-04-03 | 2026-04-05 | 2
Fabrication/stitching | 2026-04-05 | 2026-04-15 | 10
Finishing | 2026-04-15 | 2026-04-18 | 3
Packing | 2026-04-18 | 2026-04-20 | 2
Inspection | 2026-04-20 | 2026-04-22 | 2
Dispatch | 2026-04-22 | 2026-04-23 | 1